For this timeline, I would not calculate Status simply from the % column. A professional project-management application should calculate status using actual progress + schedule performance + milestone health, with the ability to override it manually when necessary.

Based on the timeline you provided, the project should currently be On Track, with a small watch item around the upcoming IT/SIT transition.

1. Recommended status model

Use four project-level statuses:

| Status | Meaning | Recommended rule |
| --- | --- | --- |
| 🟢 On Track | Progress is consistent with plan | Schedule variance ≥ -10% and no critical issue |
| 🟡 At Risk | Some slippage or risk exists | Schedule variance -10% to -20% OR upcoming milestone risk |
| 🔴 Off Track | Material delay | Schedule variance < -20% OR critical milestone delayed |
| ⚪ Not Started | Project hasn't meaningfully started | Actual progress = 0% |

I would not use "Complete" as a project status unless 100% of required work is complete.

2. First calculate task-level schedule progress

For each task, calculate:

Planned Progress

Based on today's date:

capped between 0% and 100%.

Then compare it to Actual %.

Schedule Variance

For example, your:

IT Build & Unit Test

- Start: 07/20/2026

- End: 09/18/2026

- Actual: 40%

- Today: 08/09/2026

Approximately 33% of the calendar duration has elapsed.

So:

Planned = ~33%

Actual = 40%

Therefore:

Schedule variance ≈ +7%

That's actually ahead of schedule.

3. But there is a better calculation for your application

Because your timeline contains:

- Tasks

- Milestones

- Different durations

- Different percentages

- Different owners

I recommend calculating three separate dimensions.

A. Progress

How much work has actually been completed?

B. Schedule

Are we completing the work at the rate required to meet the planned dates?

C. Milestones

Are important dates being achieved?

Then calculate overall status from those three.

4. Overall Project Progress

Don't simply average the percentages.

For example, you currently have:

Discovery                  100%

Requirements Gathering    100%

Requirements Documentation100%

IT Analysis & Design      100%

Requirement Freeze        100%

IT Build & Unit Test       40%

SIT                         0%

UAT                         0%

Go/No Go                    0%

Production Migration Prep  0%

Production Migration       0%

Production Validation      0%

Production Validation      0%

Go Live                     0%

A simple average would be misleading.

Instead, use duration-weighted progress.

For tasks:

For your timeline, the task durations shown add up to approximately 65 weeks.

Only the 9-week IT Build task currently has partial progress.

So duration-weighted completion is approximately:

≈ 67.4%

That is a much more meaningful project progress number.

However, there's an important caveat:

I would NOT necessarily display 67% as your project's progress.

Why?

Because your project is moving through sequential phases, and some later work hasn't started yet.

A better dashboard would distinguish:

Overall completion: 67%

from:

Schedule health: On Track

and:

Next milestone: SIT

This prevents users from interpreting 67% as "67% of the project is almost done" when significant implementation/testing remains.

5. Even better: use weighted task effort

If your application eventually supports it, I recommend this hierarchy:

Level 1 — Basic

Duration weighted:

Progress =

Σ(Duration × % Complete)

────────────────────────

Σ(Duration)

Level 2 — Better

Use estimated effort:

Progress =

Σ(Estimated Hours × % Complete)

──────────────────────────────

Σ(Estimated Hours)

Level 3 — Enterprise

Use:

Work × Dependencies × Critical Path × Milestones

This is where Timeline Studio could become much more powerful.

6. Status should NOT equal Progress

This is an important design decision.

For example:

Project A

Progress = 40%

Schedule = Ahead

Status = 🟢 On Track

Project B

Progress = 80%

Schedule = 20% behind

Status = 🔴 Off Track

So:

Progress tells you how much is done.

Status tells you whether the project is healthy.

Those are different things.

7. Recommended calculation for your Status column

For each task:

🟢 Complete

If:

Actual % = 100%

Then:

Complete

⚪ Not Started

If:

Actual % = 0%

AND

Start Date > Today

Then:

Not Started

🟢 On Track

If:

Actual Progress >= Planned Progress - 10%

Then:

On Track

🟡 At Risk

If:

Actual Progress < Planned Progress - 10%

but:

Actual Progress >= Planned Progress - 20%

Then:

At Risk

🔴 Off Track

If:

Actual Progress < Planned Progress - 20%

Then:

Off Track

8. But milestones need special treatment

This is extremely important for your timeline.

You have:

- Requirement Freeze

- Go/No Go

- Production Migration

- Go Live

A milestone should not use the same percentage calculation as a task.

For example:

Requirement Freeze

07/29/2026

It is already complete.

Therefore:

🟢 Complete

Go/No Go

10/16/2026

Today = 08/09/2026.

Therefore:

⚪ Not Started

But if the milestone date is approaching and its predecessor tasks aren't progressing, it could become:

🟡 At Risk

9. Add predecessor logic

This would make Timeline Studio considerably smarter.

For example:

IT Build & Unit Test

↓

SIT

↓

UAT

↓

Go / No Go

↓

Production Migration

↓

Production Validation

↓

Go Live

If IT Build is delayed, the application should examine whether that delay affects SIT.

For example:

IT Build

End: 09/18

SIT

Start: 09/14

There's actually an overlap.

That's important.

Your system should flag:

⚠️ SIT starts before IT Build & Unit Test is scheduled to finish.

That may be intentional, but the application should recognize it.

This is much more valuable than simply calculating %.

10. Critical Path should influence Status

I'd recommend a weighted status engine:

┌─────────────────┐

│ Task Progress   │

└────────┬────────┘

│

▼

┌─────────────────┐

│ Schedule Health │

└────────┬────────┘

│

┌──────────────┼──────────────┐

▼              ▼              ▼

Milestones     Dependencies   Critical Path

│              │              │

└──────────────┼──────────────┘

▼

┌─────────────────┐

│ PROJECT STATUS  │

└─────────────────┘

11. My recommended scoring engine

For Timeline Studio, I'd actually calculate a Project Health Score.

Schedule

40%

Progress

25%

Milestones

20%

Dependencies

10%

Risks/Issues

5%

Then:

| Score | Status |
| --- | --- |
| 85–100 | 🟢 On Track |
| 70–84 | 🟡 At Risk |
| <70 | 🔴 Off Track |

This gives you a much more sophisticated system than simply looking at task percentages.

12. For your current timeline

Based strictly on the screenshot:

Completed

- Discovery — 100%

- Requirements Gathering — 100%

- Requirements Documentation — 100%

- IT Analysis & Design — 100%

- Requirement Freeze — 100%

Current

IT Build & Unit Test

40% complete

But it is only about one-third through its planned calendar duration.

Therefore:

🟢 On Track

Upcoming

SIT

Starts 09/14/2026.

I'd classify it:

⚪ Not Started

but monitor the dependency on IT Build.

UAT

⚪ Not Started

Go/No Go

⚪ Not Started

Production activities

⚪ Not Started

Go Live

⚪ Not Started

13. What I would show in Timeline Studio

Instead of only this:

STATUS

[Complete]

[Complete]

[Complete]

[Complete]

[Complete]

[In Progress]

[Not Started]

...

I'd eventually have:

STATUS              PROGRESS       SCHEDULE

🟢 Complete           100%          On Plan

🟢 Complete           100%          On Plan

🟢 Complete           100%          On Plan

🟢 Complete           100%          On Plan

🟢 Complete           100%          On Plan

🟢 On Track            40%          +7% Ahead

⚪ Not Started          0%          Future

⚪ Not Started          0%          Future

🟡 At Risk              0%          Dependency Risk

...

And at the top of the project:

┌─────────────────────────────────────────────────────────┐

│ PROJECT HEALTH                                          │

│                                                         │

│ 🟢 ON TRACK                         Health Score: 91     │

│                                                         │

│ Overall Progress       67%                              │

│ Schedule Performance   +7%                              │

│ Completed Tasks        5 / 14                           │

│ Next Milestone         SIT • Sep 14                     │

│                                                         │

└─────────────────────────────────────────────────────────┘

One thing I would change in your current design

Don't allow users to manually select Complete, In Progress, and Not Started if you want Timeline Studio to be a smart planning application.

Instead, have:

Status = Auto Calculated

with an optional:

Override Status → Manual

That gives you both automation and project-manager control.

For your particular timeline, I'd implement the calculation as:

Actual % → Planned % → Schedule Variance → Milestone/Dependency Check → Status → Overall Project Health.

That is the approach I'd recommend building into Timeline Studio rather than a simple percentage-based status calculation.